## Impediments Sheet
Impediment Status | Impediment Priority Rank | Impediment Tracking Number | Impediment Title | Description | Severity | Reporter | Reported Date | Resolution Owner | Resolution Committed Date | Resolution Actual Date | Escalation Status | Escalated To | Escalation Date | Resolution Status Description
Open |  | PLC-007 | Technology approved to chase business dates with technical debt | If a business unit specifies a date and technology teams need to workaround strategic platforms that are not aligned to the delivery, they are approved to incur Technical Debt (suboptimal implementation requiring rework), without a committed plan for remediation. Example: APD IVR requires data that should be sources from the Datahub, instead it has been approved to use tactical data sources(incur Technical Debt) with no committed remediation date. | Critical | Glenn Onos | 2026-01-28 08:56 | brandy.mcnalis@protective.com |  |  | Escalated | matt.kohler@protective.com | 2026-02-04 | APD IVR tactical is cancelled. Datahub strategic is the only solution. Meeting with Tara and T-Tech to gain alignment on collaboratively moving forward planning and deployment.
Open |  | PLC-008 | AI Readiness Assessment Pushback | Human Resoures is concerned about doing an assessment and is pushing back on administering | Critical | Glenn Onos | 2026-01-28 09:37 | wade.harrison@protective.com |  |  | Escalated | wade.harrison@protective.com | 2026-02-09 | In order for Protective to be successful at Enterprise AI Adoption, it must first assess where the knowledge and experience currently stand. There are concerns from HR about creating and distributing a survey to digitally accomplish this and use the feedback for a program of improvement. Adding 5 questions to the pulse survey for all employees post March 11th.
Open |  | PLC-020 | Reschedule AI Accelerator ¦ Pod ADO Project Onboarding delayed due to Protective standards issue with Architecture team | Rescheduling pending establishment of ADO project | Critical | Finley Blake | 2026-02-09 14:49 | brandy.mcnalis@protective.com |  |  | Not Escalated | matt.kohler@protective.com | 2026-02-11 | SSA will schedule ASAP once establishment of ADO project
Open |  | PLC-021 | Inability for timely Root Cause Analysis and resolution to Authorization related requests (in this case for Mural) causing team members to not participate in time critical collaborations | It has taken over 2 days to get 10 team members granted authorization to use an existing approved commercial software tool at Protective. After two days there is still one user, authorized and using VDI and other Protective applications that has not been granted Mural access and no Root Cause Analysis has been able to trace the reason why | Critical | Glenn Onos | 2026-02-10 08:27 | brandy.mcnalis@protective.com |  | 2026-02-10 | Not Escalated |  |  | In order for there to be lasting process change, a through and transparent root cause analysis needs to be documented so future onboarding and productivity is not delayed for the same reasons.
Open |  | PLC-023 | Business leadership is not able to provided objective traceability/attribution of business goals/objectives to requests for technology products and services. | In the process of refining business objectives to be attained by completing prioritized Pod use cases is encountering difficulties in quickly gaining objective attribution of 2026 business goals with the work being prioritized for delivery. | Critical | Glenn Onos | 2026-02-10 17:20 | brandy.mcnalis@protective.com |  |  | Not Escalated |  |  | APD IVA Enhanced Consumer Experience, Sales Analytics Acceleration, UW Summarization. Next step is to follow-up with Tara Williams, Sean Plummer and Kelly stone.
Open |  | PLC-024 | For APD IVA, the Pod needs direct access to the TTec team and the requirements/planning documents used for tracking. | Instead of arbitrating access to this vendor through APD, the Pod will need direct access to collaborate with the TTec team to orchestrate development and delivery of value on shared expectations. Apparently, due to a high rate of change, the requirements/design/specifications documents being used by APD/TTec are not be shared with the Datahub team. Leading to technical debt and potential delays in meeting commitments being made without full transparency and inclusion of the critical Datahub strategic platform team. | Critical | Glenn Onos | 2026-02-10 17:27 | brandy.mcnalis@protective.com |  |  | Not Escalated |  |  | The Pod team has indicated that any meeting with TTec turned into a "coliseum" meeting with 30+ people in attendance and not effective in driving results.
Open |  | PLC-026 | Enterprise GitHub migration indicated as a technical debt dependency on getting separate ADO Project | John Byrd indicated that the enterprise is moving forward with a migration of Source Code Management activities from ADO to GitHub. A decision has been made to not incur additional technical debt by new ADO projects utilizing ADO Pipelines instead of GitHub and would require the Pod project to migrate to GitHub as a condition of the setup. | Critical | Glenn Onos | 2026-02-10 18:21 | brandy.mcnalis@protective.com |  |  | Not Escalated |  |  | Preliminary agreement with John Byrd that the Pod will consider alignment with the enterprise at the conclusion of the Pilot and before enterprise scaling. With the understanding that a GitHub owner and administrator will be able to present the feature functionality of the migration offering and fit/gap with ADO pipeline migrations.
Open |  | PLC-028 | Rajani Kokala, Pod Team Scrum Master, is not being fully dedicated to the Pod pilot team. | Reportedly, Kokala continues to be asked, by her leadership, to hold allocations of her time to APD teams and ceremonies. There continues to be discussions of a pending backfill needed before she can fully transition into the POD Scrum Master role, which has no committed end date. This is a critical impediment given the current fully dedicated startup mode needed with the Pod pilot team. | Critical | Glenn Onos | 2026-02-10 22:46 | brandy.mcnalis@protective.com |  |  | Escalated | matt.kohler@protective.com | 2026-02-10 | Rajani is trying to balance her multiple commitments and we look forward to her being fully part of the Pod team.
Open |  | PLC-029 | Protective Life employees and third-party contractors are sharing API keys, database credentials, service account passwords, and other secrets via: Microsoft Teams direct messages and Outlook emails (both internal and to external vendors) | Apparently, the Pod team, prior to establishing the Pod, has been advised to send digital keys/secrets in clear text(no encryption). This is not only a policy/procedure risk but legal/regulatory exposure as well. There should be a standard enterprise policy/procedure/platform for establishing and managing all keys/secrets. Perhaps this is just a communication/training miss and it is easily fixed. The team cannot move forward with any of the prioritized use cases without this remediated/resolved. | Critical | Glenn Onos | 2026-02-11 09:02 | brandy.mcnalis@protective.com |  |  | Not Escalated
Open |  | PLC-004 | No Documented Change Management Process | No communicated, defined ways of flowing work through the company as one team | High | Glenn Onos | 2026-01-27 23:24 | brandy.mcnalis@protective.com |  |  | Escalated | matt.kohler@protective.com | 2026-02-04 | Pod team needs specific information about interacting with existing enterprise work processes for coordination and reporting.
Open |  | PLC-015 | SSA team needs write access to new ADO project for the Pod | SSA seeks read and write ADO access and the team is unaware of the correct responsibility chain for administering ADO permissions | High | David Clark | 2026-02-09 11:23 | brandy.mcnalis@protective.com |  |  | Not Escalated |  |  | Protective Life believes administrator responsible for permissioning is Chris Lucas
Open |  | PLC-027 | Medallion Data Architecture Framework was rejected by Protective Enterprise Architecture for utilization by the Datahub. | The Pod is impacted by the EA rejection of adopting the Medallion Data Architecture Framework as foundational to the Enterprise Datahub. An executive decision will be need needed and if Protective decides on another framework an alternate will need to be indicated quickly. | High | Glenn Onos | 2026-02-10 18:26 | matt.kohler@protective.com |  |  | Not Escalated |  |  | The Pod team is digging into the archives for the disposition of this architecture decision.
Closed |  | PLC-006 | Competing Methodology Pilots - Leadership Not Aligned to this pilot due to the introduction of competing methodologies | There are pilots being conducted by several areas, no visibility into progress, iterations, and success metrics. No process or transparency into evaluation for utilization | High | Glenn Onos | 2026-01-28 08:49 | matt.kohler@protective.com | 2026-02-09 | 2026-02-09 | Escalated | wade.harrison@protective.com | 2026-02-04 | Team Topologies pilot has been stopped as of 2/9/26
Open |  | PLC-018 | Lack of Architecture guidance on utilization of Azure Foundry vs. Databricks | To Confirm: Decide upon creation and deployment of self-service models within Databricks or Azure Foundry | Medium | Finley Blake | 2026-02-09 14:34 | brandy.mcnalis@protective.com |  |  | Not Escalated |  |  | Chris Butterfield indicated willigness to take ownership of this, awaiting confirmation of more relevant party
Open |  | PLC-030 | Lack of transparency into intended GitHub Source Code Management and CI/CD migration. | There is an enterprise effort underway to migrate from ADO pipelines to GitHub for source code management and CI/CD. Without a clear runway of enterprise ownership, capabilities, and timelines, this was presented to the Pod as a dependency to get the new ADO project for the Pod to utilize, to avoid incurring technical debt of new SCM and CI/CD practices being added to ADO. The Pod agreed it would be a critical risk and impediment to move forward during the pilot and that before scaling the product operating model, these migration concerns would need to be decided. To resolve this impediment, the resolver and/or executive needs to approve that the Pod will continue with ADO pipelines on the new Pod ADO project. | Medium | Glenn Onos | 2026-02-11 09:25 | brandy.mcnalis@protective.com |  |  | Not Escalated
Closed |  | PLC-001 |  | Awaiting Protective to organize the participants needed to kickoff the Pod and start the first sprint. | Critical | Glenn Onos | 2026-01-27 17:28 | brandy.mcnalis@protective.com | 2026-02-06 | 2026-02-09 | Not Escalated |  |  | Pod kickoff completed 2/9
Closed |  | PLC-002 | Agreed upon set of Use Case Priorities | What are the 3 AI use cases? | Critical | Glenn Onos | 2026-01-27 17:34 | chris.butterfield@protective.com | 2026-02-06 | 2026-02-09 | Not Escalated |  |  | APD IVR to IVA, Select Data Mart Migration(rewording to business outcomes), UW Summarization with AI LLM
Closed |  | PLC-003 | Prioritization method | Agreement on WSJF | Critical | Glenn Onos | 2026-01-27 17:34 | brandy.mcnalis@protective.com | 2026-01-30 | 2026-01-30 | Not Escalated |  |  | SSA and PLC agreed upon WSJF formula
Closed |  | PLC-010 | Missing ADO Access | SSA has not been provided ADO access yet, leaving team unable to complete assessment of their current agile ways of working in ADO | Critical | Finley Blake | 2026-02-02 09:54 | brandy.mcnalis@protective.com | 2026-02-06 | 2026-02-09 | Not Escalated |  |  | SSA will participate in Player/Coach roles alongside Protective. SSA will need read and write access to the Protective SSA Project in Azure DevOps.
Closed |  | PLC-014 | Mural Access | Need near real time collab platform with structure content templates and collaboration functionality | Critical | David Clark | 2026-02-06 13:36 | brandy.mcnalis@protective.com |  | 2026-02-10 | Not Escalated |  |  | Mark Brandy as owner; PL has an enterprise license it just needs to go through IT provisioning, Jason Bowles indicated we are being granted licenses afternoon (2/9). All Pod team members have access to Mural 2/10
Closed |  | PLC-019 | Reschedule AI Accelerator ¦ Pod Mural Onboarding delayed due to Protective permissions delays for Pod team | Rescheduling, pending Mural access established | Critical | Finley Blake | 2026-02-09 14:49 | brandy.mcnalis@protective.com |  | 2026-02-10 | Not Escalated |  |  | SSA will schedule ASAP once Mural access established; Jason Bowles indicated we are being granted licenses afternoon (2/9). 2/10 all Pod team members have been granted access.
Closed |  | PLC-022 | No visibility into OOO plans for team members for the next 90 days | Sprint planning and execution are only days away and there is no centralized information to show intended OOO for each of the team members. | Critical | Glenn Onos | 2026-02-10 08:31 | jamie.heard@protective.com | 2026-02-11 | 2026-02-10 | Not Escalated |  |  | Jamie Heard has provided this on Teams channel on 2/10/26
Open |  | PLC-032 | Unable to offer Disaster Recovery | Disaster Recovery cannot be configured in the paired region due to the absence of a firewall. Without network security infrastructure in the paired region, secure failover and recovery operations are not possible. This is an enterprise wide constraint. | Critical | Glenn Onos | 2026-02-11 18:35 | brandy.mcnalis@protective.com